## SCHOOL CALENDAR (hidden)
LOT 2: ECOLE PRESBYTERAL ANSE A VEAU
SINGLE STOREY 6 CLASSROOMS BILL OF QUANTITIES
A. BOQ using CRS Design
Item No. | Description | Qty | Unit | Mois1 |  |  |  | Mois2 |  |  |  | Mois3 |  |  |  | Mois4 |  |  |  | Mois5 |  |  |  | Mois6 |  |  |  | Mois7
|  |  |  | S1 | S2 | S3 | S4 | S5 | S6 | S7 | S8 | S9 | S10 | S11 | S12 | S13 | S14 | S15 | S16 | S17 | S18 | S19 | S20 | S21 | S22 | S23 | S24 | S25 | S26 | S27 | S28
1 | General Requirements | bar: Mois1 S1 to Mois1 S4
| Mobilization & Demobilization | 1 | lot | bar: Mois1 S1 to Mois1 S2
| Temporary facilities, office & storage | 1 | lot | bar: Mois1 S1 to Mois1 S2
| Health and Safety | 1 | lot | bar: Mois1 S2 to Mois1 S4
| Testing of Materials | 1 | lot | bar: Mois1 S2 to Mois1 S4
2 | Earthworks
| Site layout | 1 | lot | bar: Mois1 S3 to Mois2 S5
| Excavation | 82 | m3 | bar: Mois1 S3 to Mois2 S5
| Backfilling and compaction | 73.15 | m3 | bar: Mois1 S3 to Mois2 S5
| Demolition of rock, if applicable (if not applicable=0) | 1 | lot | bar: Mois1 S3 to Mois2 S6
| Hauling and disposal of excess rubbles | 1 | lot | bar: Mois1 S3 to Mois2 S6
3 | Concrete Works | bar: Mois2 S5 to Mois2 S8
| Foundation, concrete mix:1:2:3, this includes steel bars and forms | 8.85 | m3 | bar: Mois2 S5 to Mois2 S7
| Columns, concrete mix:1:2:3, this includes steel bars and forms | 12.7 | m3 | bar: Mois2 S5 to Mois2 S7
| Lintel Beams, concrete mix:1:2:3, this includes steel bars and forms | 0.6 | m3 | bar: Mois2 S7 to Mois2 S8
| Roof beam, concrete mix:1:2:3, this includes steel bars and forms | 19.25 | m3 | bar: Mois2 S7 to Mois2 S8
| Slab on grade (SOG), 125mm thk, concrete mix 1:2:4. This includes steel bars and formworks | 45.1 | m3 | bar: Mois2 S8 to Mois3 S10
| Power float direct cement finish for SOG | 360.36 | m2 | bar: Mois2 S8 to Mois3 S10
4 | Masonry Works | bar: Mois3 S9 to Mois4 S13
| Wall footing, concrete mix 1:2:3. This includes steel bars and formworks | 12.25 | m3 | bar: Mois3 S9 to Mois3 S10
| 6" concrete hollow blocks (CHB) with D-10 vertical steel bars at 0.90m and D-10 horizontal bars at every 3 layers | 667.5 | m2 | bar: Mois3 S10 to Mois3 S11
| Plastering works, 20mm thk, class A, 1:3 cement sand ratio | 854.52 | m2 | bar: Mois3 S11 to Mois4 S13
5 | Roof works | bar: Mois4 S13 to Mois4 S16
| Roofing sheets, 3'x12' gauge 29 | 202 | pcs | bar: Mois4 S13 to Mois4 S14
| Umbrella Roof nail | 100 | kg | bar: Mois4 S13 to Mois4 S14
| Roof insulation, 12mm thk ACI insulationwith aluminum foil on one side | 531 | m2 | bar: Mois4 S14 to Mois4 S15
| Fabrication, assembly & trusses installation | 1 | lot | bar: Mois4 S14 to Mois4 S15
6 | Painting works, 3 coats of emulsion paint (submit sample for CRS Engineer approval) | 854.52 | m2 | bar: Mois4 S16 to Mois5 S18
7 | Doors and Windows | bar: Mois5 S18 to Mois6 S21
| Steel doors including locksets and hinges( double panel) | 12 | sets | bar: Mois5 S19 to Mois5 S20
| Steel doors including locksets and hinges( single panel) | 1 | sets | bar: Mois5 S20 to Mois6 S21
| Louver blocks (submit sample for CRS Engineer approval) | 105 | m2 | bar: Mois5 S20 to Mois6 S21
8 | Rain water harvesting system | bar: Mois6 S21 to Mois6 S22
| Roof gutter- (only at the back) | 63 | lm | bar: Mois6 S22
| 4" diam PVC pipes including fittings | 1 | lot | bar: Mois6 S22 to Mois6 S23
| Water storage tank 500 gals capacity including concrete base | 1 | set | bar: Mois6 S23 to Mois6 S24
| Tap stand with 4 faucet, concrete base | 1 | lot | bar: Mois7 S25
| Soak pit including drainage from tapstand to soak pit | 1 | lot | bar: Mois7 S25 to Mois7 S26
9 | Miscellaneous work ( any activities not listed above but needed to complete the work) | 1 | lot | bar: Mois7 S25 to Mois7 S26
VERIFICATION AND ERROR CORRECTION IF APLICABLE | bar: Mois7 S27
RECEPTION PROVISORY | bar: Mois7 S26
RECEPTION DEFINITIVE | bar: Mois7 S28
DEMOBILIZATION
SCHOOL CALENDAR CONSTRUCTION

## Summary
LOT 2: ECOLE PRESBYTERAL ANSE A VEAU
SINGLE STOREY 6 CLASSROOMS BILL OF QUANTITIES
A. BOQ using CRS Design
Lot | Description | Qty | Unit | Unit rate | Amount
1 | One(1) storey 1 classrooms with 1 office | 1 | lot | 0 | 0
2 | Six (6) cubicles latrine with water storage and washing station | 1 | lot | 0 | 0
3 | Work remaining on the first four classrooms already built | 1 | lot | 0 | 0
| Total Cost |  |  |  | 0

## School BOQ (Lot 1)
LOT 2: ECOLE PRESBYTERAL ANSE A VEAU
SINGLE STOREY 6 CLASSROOMS BILL OF QUANTITIES
A. BOQ using CRS Design
Item No. | Description | Qty | Unit | Unit rate | Amount
1 | General Requirements
| Mobilization & Demobilization | 1 | lot |  | 0
| Temporary facilities, office & storage | 1 | lot |  | 0
| Health and Safety | 1 | lot |  | 0
| Testing of Materials | 1 | lot |  | 0
2 | Earthworks
| Site layout | 1 | lot |  | 0
| Excavation | 31.5372 | m3 |  | 0
| Backfilling and compaction | 137.4984 | m3 |  | 0
| Demolition of rock, if applicable (if not applicable=0) | 1 | lot |  | 0
| Hauling and disposal of excess rubbles | 1 | lot |  | 0
3 | Concrete Works
| Foundation, concrete mix:1:2:3, this includes steel bars and forms | 3.31 | m3 |  | 0
| Columns, concrete mix:1:2:3, this includes steel bars and forms | 6.57 | m3 |  | 0
| Lintel Beams, concrete mix:1:2:3, this includes steel bars and forms | 0.23076 | m3 |  | 0
| Roof beam, concrete mix:1:2:3, this includes steel bars and forms | 7.4036 | m3 |  | 0
| Slab on grade (SOG), 125mm thk, concrete mix 1:2:4. This includes steel bars and formworks | 15.1125 | m3 |  | 0
| Power float direct cement finish for SOG | 120.9 | m2 |  | 0
4 | Masonry Works
| Wall footing, concrete mix 1:2:3. This includes steel bars and formworks | 3.332 | m3 |  | 0
| 6" concrete hollow blocks (CHB) with D-10 vertical steel bars at 0.90m and D-10 horizontal bars at every 3 layers | 234.2925 | m2 |  | 0
| Plastering works, 20mm thk, class A, 1:3 cement sand ratio | 299.9365 | m2 |  | 0
5 | Roof works
| Roofing sheets, 3'x12' gauge 29 | 90 | pcs |  | 0
| Umbrella Roof nail | 38 | kg |  | 0
| Roof insulation, 12mm thk ACI insulationwith aluminum foil on one side | 250 | m2 |  | 0
| 2"x6"x16' top & bottom chord & rafters | 64.98 | pc |  | 0
| 2"x6"x14' top and bottom chord | 14.82 | pc |  | 0
| 2"x6"x12' top and bottom chord | 3.8 | pc |  | 0
| 2"x6"x10' top and bottom chord | 3.8 | pc |  | 0
| 2"x4"x16' web members | 7.6 | pc |  | 0
| 2"x4"x14' web members & purlins | 80.56 | pc |  | 0
| 1/2"thk.x4'x8' gusset plate | 10.64 | pc |  | 0
| 4" CWN | 38 | kg |  | 0
| 3" CWN | 28.5 | kg |  | 0
| 2" CWN | 19 | kg |  | 0
| Fabrication, assembly & trusses installation | 1 | lot |  | 0
6 | Painting works, 3 coats of emulsion paint (submit sample for CRS Engineer approval) | 113.9759 | m2 |  | 0
| - Painting of Handrails at ramp, stair and hallway | 39.46 | ml |  | 0
7 | Doors and Windows
| Steel doors including locksets and hinges( double panel) | 4 | sets |  | 0
| Steel doors including locksets and hinges( single panel) | 1 | sets |  | 0
| Louver blocks (submit sample for CRS Engineer approval) | 40.383 | m2 |  | 0
8 | Rain water harvesting system
| Roof gutter- (only at the back) | 24.2298 | lm |  | 0
| 4" diam PVC pipes including fittings | 0.3846 | lot |  | 0
| Water storage tank 500 gals capacity including concrete base | 2 | set |  | 0
| Tap stand with 4 faucet, concrete base | 1 | lot |  | 0
9 | Ramp, Stair
| Construction Handrails at ramp, stair and hallway | 39.46 | ml |  | 0
| Concrete walkway . Use 2 m width of walkway | 20.0916 | m3 |  | 0
| Walkway (2.00m wide) to be built from the main gate walking past the classroom and on to the toilet block. | 167.43 | m2 |  | 0
| Main gate (4.5 m wide, demolish part of the existing fence, place two columns to hold the gate and connecting masonry wall) | 1 | Unit |  | 0
9 | Miscellaneous work ( any activities not listed above but needed to complete the work) | 1 | lot |  | 0
| Sub-total cost (sum of item 1-9) |  |  |  | 0
10 | Contingency cost (5% of sub-total cost) |  |  | 0.05 | 0
11 | Contractor's overhead and profit (10% of sub-total cost) |  |  | 0.1 | 0
| Total Cost |  |  |  | 0

## Latrine BOQ (Lot 2)
LOT 2: ECOLE PRESBYTERAL ANSE A VEAU
Six (6) Cubicles latrine with rain water harvesting and wash station
Item No. | Description | Qty | Unit | Unit rate | Amount
1 | General Requirements
| Mobilization & demobilization | 1 | lot |  | 0
| Site safety measures | 1 | lot |  | 0
2 | Sub-structure works
| Site Layout | 1 | lot |  | 0
| Excavation Septic tank, including backfilling, compaction & removal of excess soil | 38.54 | m3 |  | 0
| Footing, wall footing, columns, concrete, floor beams and floor slab mix:1:2:3 (fc'=3,000 psi), including steel bars and formworks | 9.7225 | m3 |  | 0
| CHB wall, 8" thk, 500 psi compresssive strength | 32.705 | m2 |  | 0
| Cement plaster, 18mm thk 1:3 cement sand ratio | 32.705 | m2 |  | 0
| Supply and installation of 4" diameter SCH40 PVC vent pipe with 4" cap and a wire screen at the end of the PVC. | 15 | meters |  | 0
3 | Superstructure (Above ground structure)
| 6" thk CHB with D-10mm diam vertical bars @ 0.90m and D-10 horizontal bars @ every 3 layers | 62.41 | m2 |  | 0
| Concrete works for columns, roof beam, lintels, concrete mix: 1:2:3 (fc'= 3000psi) including steel bars and formworks | 1.752 | m3 |  | 0
| Wall plastering, 1:3 cement sand ratio, 18mm thk | 124.82 | m2 |  | 0
| Construction of 2 disabled friendly cubicles at both end including floor mounted grab bar | 2 | unit |  | 0
4 | Roof Works
| 2"x4" wood rafter achored to the wall, 2"x3" wood purlins, 1"x6" facia board, CGI gauge 29 roof sheets with roof umbrella nail, roof gutters all in accordance with the approved design drawings | 21.93 | m2 |  | 0
Note: all wood shall be termite protected
5 | Finishes
| Metal doors with metal door jambs, including complete accessories such as hinges, door locks(contractor shall submit shop drawing or catalog prior to purchase) | 6 | sets |  | 0
| Supply and installation of louver windows (submit sample of louver blocks for CRS Engineer approval) | 1 | lot |  | 0
| Painting works, 3 coats of weathercoat paint (seek CRS approval for the brand of paint and its color) | 124.82 | m2 |  | 0
| Supply and installation of latrine seat (seek approval from CRS Engineer) | 6 | unit |  | 0
| Construction of disabled friendly ramps including handrail as per approved drawings | 1 | lot |  | 0
| Demarcation of doors indicating 3 for girls and 3 for boys (paint or other signage material) | 6 | sets |  | 0
| Installation of floor drains with scupper drain at the back directly discharging to soak pit | 6 | sets |  | 0
4 | Sanitary Drainage System
| Purchase and installation of toilets (CORONA type) and necessary accessories | 6 | Lot |  | 0
5 | Rain water catchment system (water supply)
| Construction of handwashing station with concrete base as per design drawing | 1 | lot |  | 0
| Construction of concrete tank base and supply of 500 gals PVC tank | 2 | lot |  | 0
| Supply and installation of roof gutter with complete PVC pipes | 1 | lot |  | 0
| Soak away pit including drainage from washing station to soak pit | 1 | lot |  | 0
| Sub-total cost (sum of item 1-5) |  |  |  | 0
5 | Contingency Cost (5% of sub-total cost) |  |  | 0.05 | 0
6 | Contractor's overhead and profit (10% of sub-total cost) |  |  | 0.1 | 0
| Total Cost |  |  |  | 0
0.05

## Travaux restant (Lot 3)
LOT 2: ECOLE PRESBYTERAL ANSE A VEAU
Correction des travaux de finition
Item No. | Description | Qty | Unit | Unit rate | Amount
1 | Concrete Works
| Power float direct cement finish for SOG | 221.7295 | m2 |  | 0
2 | Masonry Works
| Roofing sheets, 3'x12' gauge 29 | 124.2906 | pcs |  | 0
| Umbrella Roof nail | 61.53 | kg |  | 0
| Roof insulation, 12mm thk ACI insulationwith aluminum foil on one side | 326.7243 | m2 |  | 0
| 2"x4"x14' web members & purlins | 32.754 | pc |  | 0
3 | Painting works, 3 coats of emulsion paint (submit sample for CRS Engineer approval) | 525.7862 | m2 |  | 0
4 | Doors and Windows
| Steel doors including locksets and hinges( double panel) | 8 | sets |  | 0
5 | Rain water harvesting system
| Roof gutter- (only at the back) | 38.7702 | lm |  | 0
| 4" diam PVC pipes including fittings | 0.6154 | lot |  | 0
6 | Doors and Windows
a | Correction et finition des claustras | 1 | lot |  | 0
b | Correction des pignons | 1 | lot |  | 0
c | Soudure general de la structure metallique du batiment I | 1 | lot |  | 0
| Sub-total cost (sum of item 1-4) |  |  |  | 0
7 | Contingency Cost (5% of sub-total cost) |  |  | 0 | 0
8 | Contractor's overhead and profit (10% of sub-total cost) |  |  | 0 | 0
| Total Cost |  |  |  | 0